## Action plan
Corners - action plan, autumn 2026 pilot (Bilbao)
Drafted 29 September 2026 - departments: Audience, Operations, Product - fill the yellow Owner cells with a name, not a team
Action | Department | Owner | Start date | Deadline
Install Unera and write a competitor teardown of its Bilbao page | Audience | Audience lead | 2026-09-29 | 2026-10-06
Record sign-up source at the point of capture (code, chat, card, invite, word of mouth) | Audience | Audience lead | 2026-09-29 | 2026-10-02
Show up honestly in the Erasmus Bilbao 2026 group chats and r/Erasmus | Audience | Audience lead | 2026-09-29 | 2026-10-09
Write the persona-to-channel brief (Chiara / Aiyana / Marta) | Audience | Audience lead | 2026-10-01 | 2026-10-09
Set the growth baseline and propose the first targets (no targets before 8 Oct) | Audience | Audience lead | 2026-09-29 | 2026-10-08
Run Instagram and TikTok to the 70/25/5 content split, one format named per post | Audience | Audience lead | 2026-09-29 | 2026-10-22
Book partner conversations: one ESN section, one provider, one international office | Audience | Audience lead | 2026-09-29 | 2026-10-15
Pitch two partners and get a cohort code into one welcome email | Audience | Audience lead | 2026-10-05 | 2026-10-22
Write up the block 2 campaign for mini-project one | Audience | Audience lead | 2026-10-12 | 2026-10-22
Measure cohort conversion: the share of a partner cohort who joined within two weeks | Audience | Audience lead | 2026-10-22 | 2026-11-10
Open January pre-registrations and read the spring waitlist weekly | Audience | Audience lead | 2026-10-12 | 2026-12-03
Sign one institution for the January arrival wave | Audience | Audience lead | 2026-11-17 | 2026-12-03
Write the moderation plan - anonymous posting cannot launch without it | Operations | Operations lead | 2026-09-29 | 2026-10-12
Stand up the hours sheet and the same-day logging rule | Operations | Operations lead | 2026-09-29 | 2026-10-01
Stand up the pilot sheet: sign-ups, source, activation within 48h, weekly actives | Operations | Operations lead | 2026-09-29 | 2026-10-02
Bring three name, handle and domain options with availability checked | Operations | Operations lead | 2026-09-29 | 2026-10-08
Restructure the repo to the corners-connect layout and protect main | Operations | Operations lead | 2026-09-29 | 2026-10-10
Set the cost baseline: two weeks of logged hours per active student | Operations | Operations lead | 2026-09-24 | 2026-10-08
Build the field rota for residences, libraries and Spanish courses | Operations | Operations lead | 2026-10-01 | 2026-10-22
Place partner cafe cards for the week's meeting spot | Operations | Operations lead | 2026-10-05 | 2026-10-22
Read delivery at every session: committed, shipped, slipped twice | Operations | Operations lead | 2026-09-29 | 2026-12-03
Verify or replace every example price, date and opening day on the site | Operations | Operations lead | 2026-10-05 | 2026-11-17
Automate the pilot with Make/n8n and move the data into Supabase | Operations | Operations lead | 2026-10-27 | 2026-11-10
Check GDPR for student emails and posts: minimum data, in the EU, no names in the repo | Operations | Operations lead | 2026-10-27 | 2026-11-17
Report the automation dividend: hours saved per week against the block 2 baseline | Operations | Operations lead | 2026-11-10 | 2026-11-17
Print and place residence welcome cards with a QR for the January wave | Operations | Operations lead | 2026-11-17 | 2026-12-03
Take open decision 1 to a vote: the whole feature set, or Nearby and Recs first | Product | Product lead | 2026-09-29 | 2026-10-06
Adopt the north star definition and start asking the weekly find question | Product | Product lead | 2026-09-29 | 2026-10-02
Merge the two city datasets into one shared/cities.js (ten cities against six) | Product | Product lead | 2026-09-29 | 2026-10-10
Move every palette into shared/theme.css as the single source of truth | Product | Product lead | 2026-10-01 | 2026-10-10
Reconcile the housing mock-up's tab bar with the app's information architecture | Product | Product lead | 2026-10-01 | 2026-10-15
Put a provenance chip on every number: Sourced, Calculated, Our rating, Mock, Not researched | Product | Product lead | 2026-10-05 | 2026-10-22
Bring every published rec up to a price, a time and a student-rate tag | Product | Product lead | 2026-09-29 | 2026-10-22
Replace the base64 photos.js with shared/photos/*.jpg and plain img tags | Product | Product lead | 2026-10-12 | 2026-10-27
Build what the pilot proved: sign-in, the feed, recs, the programme page | Product | Product lead | 2026-10-27 | 2026-11-10
Ship the invite mechanic with the MVP | Product | Product lead | 2026-10-27 | 2026-11-10
Connect the waitlist form to a real backend | Product | Product lead | 2026-10-27 | 2026-11-10
Take the first real week-4 retention read off the event log | Product | Product lead | 2026-11-10 | 2026-11-17
Bring Housing into the app, or document why it stays website-only | Product | Product lead | 2026-11-17 | 2026-12-03

## Notes & sources
How to use this sheet
Legend - which cells to edit
Owner (yellow) | The only column you must fill in. Replace the role placeholder with one person's name. The KPI tree rule is 'not a team that agrees to look at it - a name'.
Department | Pick from the dropdown: Audience, Operations, Product. The row shading follows the department - blue, grey, green.
Start date / Deadline | Editable, formatted dd mmm yyyy. Everything else can stay as drafted.
Example row | Action: Write the moderation plan ¦ Department: Operations ¦ Owner: Marta Ruiz ¦ Start: 29 Sep 2026 ¦ Deadline: 12 Oct 2026
Where the dates come from (course calendar, PROJECT.md section 2)
Block 2 | 24 Sep - 22 Oct 2026. Mini-project one due 22 Oct, 20%.
Block 3 | 27 Oct - 10 Nov 2026. Mini-project two due 10 Nov, 20%.
Block 4 | 17 Nov - 3 Dec 2026. Final project due 3 Dec, 20%.
Jan-Feb 2027 | The spring arrival wave, the first launch that isn't a pilot. Its preparation is staged inside block 4.
8 October 2026 | No KPI targets before this date (docs/kpi-tree.md section 10.4). The baseline actions are dated to land on it.
Assumptions - read before working from this
Owners are placeholders | The team is twelve people and no names appear in the repo, so every Owner cell holds a role, not a person. Assigned by Claude and to be replaced before the plan is used.
Actions are drafted, not voted | Under the decision system every item here is a pitch: approve, amend, park, reject or counter-pitch. Nothing in this sheet is binding.
Department split | Product builds the app. Audience runs marketing and partner pitches. Operations runs the pilot, moderation and data (PROJECT.md section 3).
Ongoing work | Where an action runs continuously - social posting, the weekly delivery read - the deadline is the end of its block or the end of term, not a one-off delivery date.
Sources | Every action traces to PROJECT.md (section 4 the product, 6 the marketing calendar, 8 open decisions, 9c the repo proposal, 10 the before-launch list) or docs/kpi-tree.md (sections 3-6 indicators, 8 what is countable when).
Count of actions
Audience
Operations
Product
Total